## Sheet1
Proyectos de desarrollo de software y aplicaciones
Prioridad | Prioridad/Desarrollador | Proyectos | Responsible | Beneficio | Fuente | Entregable | Soporte | Description | Status/fase | ECD | Owner
1 | 1 | CR Kaizen PA | J.Gomez | Updating the process in wich CR and CCR are made for faster CR and their documentation | FMP, Power link and user inputs, Kaizen meeting notes | A Web application that helps users build CR based on forms and on user sessions | J.Gomez | Web Application that helps users generate CRs and their follow up through email notifications | Development | 2022-11-30 | T.Schultz
1 | 1 | FMP/Variance Process Flow | J.Gomez | Track variances and part numbers affected by changes | variance logs | A file maker application that helps track variances for incoming inspection and all affected parts | Jgomez | A variance tracker for app for Incoming inspection | Development | 2022-09-30 | T.Schultz | Fases de Proyecto
1 | 1 | FMP/WebApp/Tender Request Form | J.Gomez | Contributes to OTD by giving users a notification system for tenders that don’t receive attention within their due dates, Also contributes to have a complete and historic database for analysis with won/ lost tenders | Requests by customer service | App that generates reports on lost/won tender requests. A notification system for tenders that need attention. | J.Gomez | Database on Tender Requests Won and Lost for analysis, this app will let Customer Service know when a client accepted their offer or rejected it and why (Price, delivery dates, etc) it also sends notifications when a tender has not been set . | Development | 2022-11-30 | M.Miller | Analisis | Desarrollo | Prototipo | implementacion | Seguimiento
1 | 1 | Employee Distribution Barcode Scanner App | J.Gomez | Have accurate data on employee distribution | Scanner inputs and Tempus Data | Web app to track user distribution by planning group, and location | J.Gomez | Application that lets users track employee distribution | Development | 2022-09-14 | F.Nava
1 | 1 | FMP/Enviromental Incident Report | J.Gomez | Track enviromental incidents causes and solutions | Requests by quality and FMP databases | File Maker Application that stores all enviromental incidents with affected areas and containment actions with reports with tracking numbers | J.Gomez | Filemaker Database and layout to track enviromental incidents, reports on all data entered | Implementation | 2022-06-30 | A.Duran | Analisis | Desarrollo | Prototipo | implementacion | Seguimiento
2 | 1 | HR X Hr V.2 | M.Campos | Hour by Hour tracking of assembly progress contributes with OTD 88% and efficiency measurement | Production plan, button and sensor inputs | Efficiency reports by plant and cell, electronic displays on production floor, web app for monitoring production output | J.Gomez | Develop and implement an electronic system to capture and display the production outcome and reflect the progress to the production plan every hour. | Follow up | 2022-06-30 | F.Nava
1 | 2 | Mold Mac/Ddtool (Kaizen Event tool) | J.Gomez | Contributes to OTD by allowing engineering and molding personnel enter SUPs and their inserts, also request them to toolcrib without the need of having to print and deliver the request personally, this app works in real time and replaces the old MoldMac database | Mold and insert Database | An application where all molding techs can find molds and their inserts and request them in realtime this database is working with the best SQL engine so its easy to maintain and wont go out of date | J.Gomez | Update the Mold Mac Sytem to new tech stack compatible with our new system allowing requests in real time and a maintanable and modern database | Implementation | 7/20/2022 (finished developing working on uploading sup data) | S.Ruiz
2 | 2 | Medcomp CNC KPI Measuring Tool | J.Gomez | Track Medcomp CNC KPI (Eff, Downtimes, Machine usage) | Sarah Landis KPI reports, and Medcomp FMP database | App that lets users input their production vs a calcualted optimal value to calcualte efficiency and input downtimes | J.Gomez | Application that lets users input production records, downtimes and calculates KPI for their CNC machines | Implementation | 2022-08-30 | Sarah Landis
2 | 2 | factors that improve efficiency - Data Capture | M. Campos | record of the factors that decrease efficiency, it will help to find root causes of inefficiency and to take decisions to improve and resolve issues | Production Supervisors observations | A web app for registration of factors | J.Gomez | A web app for registration of factors | Development | 9/22/2022 Phase 1 Finished ECD Phase 2: Charts and Reports 10/10/2022 | J. Esquer
1 | 2 | Andon Tools (Kaizen Event Tools Montar e iniciar) | J.Gomez | Contributes to OTD by adding validation and new modules to andon | Kaizen Event Instructions and Andon database | New andon modules and edits to current modules: 1.When starting a setup a priority must be given so molding tech knows where to start, 2. A new module for mold request was added so techs know what part number is coming and when to have mold ready. 3.After finishing a setup (montar e iniciar) quality is called so they can check the first 10 pieces 4.Predictive input for part number makes user error less common and allows for better reporting on downtimes, 5.Showing part numbers to responders allows for quicker response and actions | J.Gomez | Update the Mold Mac Sytem to new tech stack compatible with our new system allowing requests in real time and a maintanable and modern database | Implementation | 7/15/2022 (Finished developing; actions 1,2,4 and 5 already in use, action 3 will start training for quality employees | S.Ruiz
3 | 1 | Final Inspection | E.Jauregui | Contributes to OTD by providing standard time for final inspection on each of its phases or steps (Order inspection, order release and order closing) currently QA does not have a standard time reference for inspection | Inspection requests by production, QA inspection data. | Reports with times between phases and a list of inspected materials | J.Gomez | Develop a database for Final Inspections orders and releasing,eventually reducing inspection times based on data gathered | Follow up | 9/30/2022 Finished Early | L.Juarez
3 | 2 | Point Medical SOP Reference videos | J.Gomez | Show referece videos for operations done in Point Medical to help operators get a better understanding of their operations | Videos provided by Point Medical Engineering | A web app with reference videos and searchable video menu based on SOP name | J.Gomez | A knowledge system for operators in Point Medical | Implementation | 2022-04-14 | Andrew Wintek
4 | 2 | AIL Electrico | M.Campos | Web portal where all users have and can track their AIL's in one place without the need for excel files, the system has a escalation method when actions are overdue. | Ail actions on all of MMW spectrum | Ail reports and action tracking, escalation in one place. | J.Gomez | A system that has all of employees actions and sends reminders on the ECD, it also allows for system administrators to update action status | Implementation | 2022-10-22 | S.Tirado
5 | 3 | Auditorias de Entrenamiento | M.Jauregui | Training audit data in digital form | Production Audits | A database application that makes data entry easier and reporting easier | E.Jauregui | Training routers for production operators to assure updated training | Development | 2022-10-15 | D.Real
6 | 4 | One work order flow | M.Campos | Tracking orders in wip to assure a constant material stock, buffers provided by planners | XA Reports and order status code | Data on screen in production floor | J.Gomez | Database (orders in WIP tracking) | Development | 2022-12-30 | R.Godoy
7 | 3 | Bolsa de trabajo | E.Jauregui | Database on employee certifications and qualifications to fill job positions, also a knowledge base on users looking to move to a different position | Employees input, HR requirements for job positions | Smart Report to get most qualified employees for open jobs positions | J.Gomez | Report to get a most qualified employees for open job position | Follow up | 9/30/2022 Finished Early | R.Perea
8 | 9 | CBT V.2 | M.Campos | Better reporting system (Custom report builder), Better quality videos, Faster performance. | Framing videos provided by departments, report specifications provided by HR | Customizable reports, better user interface | J.Gomez | Improve reporting system | Development | 2022-12-30 | R.Perea
|  | CCR Reporting | J.Gomez | Helps users generate their own reports in filemaker pro | File Maker Pro Database: CCRs | Customizable reports | J.Gomez | A reporting system for ccrs that doesn’t need to be operated by IT personnel | Development | 2022-08-01 | D.Witt
|  | Document Training Form (File Maker) | J.Gomez | Meet docment control and training requirements | File Maker Pro Database: Training | Modified form to include training duration for all training documents | J.Gomez | updating training forms to meet quality requirements | Implementation | 2022-05-15 | D.Real
9 | 10 | Score Card Electronico | M.Campos |  |  |  |  | Assure updated records and reliable data from TIERs | Analysis | 2022-12-30 | C.Zepeda
TBD |  | maintenance knowledge system | M.Jauregui
TBD | 4 | Bar Code System Reader | M.Jauregui | Helps OTD by tracking WO and their status in real time | Bar code entry | Data on screen in production floor and web application reporting system | J.Gomez | Accuracy on Data enter for material tracking | Development | 2022-12-30 | R.Godoy
TBD | 5 | Ergonomic Tracking System | M.Campos |  |  |  |  | Lack of controls on the ergonomic risks identified performing repetitive activities. | Analysis |  | G. Guevara
TBD | 5 | Ideas V.2 | M.Jauregui | Web portal where operators have an oportunity to showcase ideas to better our proceeses | User inputs | A report with ideas to better our processeces | J.Gomez | Improve reporting system and assure production employe can insert records | Analysis |  | M.Salazar
TBD | 6 | Cost Request System V.2 | M.Campos | OTD on delivery of costing requests by costing engineering | User inputs, Engineering costing data | Web portal and user notifications for costing requests |  | Fix descripancies on data base records found in V.1 | finished developing requested changes, testing changes |  | Tanya
|  | Mtto Andon Mxli | J.Gomez |  |  |  |  | Assure app uptime | Follow up
|  | Mtto Andon PA | J.Gomez |  |  |  |  | Assure app uptime | Follow up
|  | Mtto CBT | J.Gomez |  |  |  |  | Assure app uptime | Follow up
|  | Mtto Tool Crib | J.Gomez |  |  |  |  | Assure app uptime | Follow up
|  | Mant. Servidor Exchange | M.Campos |  |  |  |  | Assure app uptime | Follow up
10 | 2 | Building Access Control Software | J.Gomez | To keep a digital record of all employees and visitors entering all MMW facilities. More efficient registration process at gates. Been able to track days in plant of foreign employees. Traceability of visitors. Ensure your visitors are authorized to be in your workplace | User Inputs | Electronic Visitor's and employees log Foreign eployees days in plant report. | M.Campos/E.Jauregui | A system to register all incoming visitors and employees and traceability that allows dowloading reports. | Analysis | 2022-10-24 | J.Guevara